SECTION – V

SPECIAL CONDITIONS OF CONTRACT (SCC)

SPECIAL CONDITIONS OF CONTRACT (SCC)

The following bid specific data for the Goods and Related Services to be procured shall amend and/or supplement the provisions in the General Conditions of Contract (GCC).

| Sl. No. | GCC Clause Ref. No. | Amendment/Supplement to GCC |
| --- | --- | --- |
|  | GCC A1.1(g) | Replace GCC A1.1(g) with the following: “Contract Price” means the sum specified in Clause 2.1 of Article 2 (Contract Price) of the Contract Agreement, subject to such additions and deductions therefrom, as may be made pursuant to the Contract. While identifying the Contract Price in Clause 2.1 of Article 2 of the Contract Agreement, an additional amount of 10% of the Contract Price shall be added to factor in escalation/Price adjustment. For the purpose of Liquidated Damages and Contract Performance Guarantee, the “Contract Price” means the sum specified in Clause 2.1 of Article 2 (Contract Price) of the Contract Agreement excluding the amount specified in lieu of Price Adjustment. |
|  | GCC A1.1 (k) | Supplementing Sub-Clause GCC 1.1(k) The delivery schedule (i.e., Receipt at Site) for the Goods and Related Services to be supplied under the subject packages shall be as follows: Mile Stones; Duration in days from the effective date of Contract (date of Notification of Award); Conductor Quantity to be supplied in Km; Cumulative Conductor Quantity to be supplied in Km; Remarks. Delivery of Goods by the Supplier at final destination site for Conductor Package - CD01 (Spec. No.: CC/NT/G-COND/DOM/A02/25/01011):. 1st; 135 days; 500 Km; 500 Km; The Bidder/Supplier is required to supply the Quantity mentioned as per time schedule. The quantities mentioned are minimum i.r.o each milestone, however, bidder/Supplier may supply additional quantities i.e. upto 2799 Km.. 2nd; 180 days; 1000 Km; 1500 Km. 3rd; 270 days; 1299 Km; 2799 Km. Total Conductor Quantity to be supplied; 2799 Km; 2799 Km. |
|  | GCC 1.1(t) | Supplementing Sub-Clause GCC 1.1(t) The Owner is: SJVN Arun-3 Power Development Company Pvt. Ltd. (SAPDC), Madhyapur (Thimi) Municipality, Ward No. 16, Swagat Marg, House No. 3, Lokanthali, P.O. Box 5685, Kathmandu Kind Attn.: Mr. Prashant Sharma, CEO -SAPDC Ph: 9852099810 |
|  | GCC 1.1(w) | Supplementing Sub-Clause GCC 1.1(w) The Purchaser is: SJVN Arun-3 Power Development Company Pvt. Ltd. (SAPDC), Madhyapur (Thimi) Municipality, Ward No. 16, Swagat Marg, House No. 3, Lokanthali, P.O. Box 5685, Kathmandu Kind Attn.: Mr. Prashant Sharma, CEO -SAPDC Ph: 9852099810 |
|  | GCC 1.1 (ee) | Add new sub clause GCC 1.1 (ee): For the purpose of the contract, the pre-award activities shall be performed by the Consultant “for and on behalf of the Owner” except in cases where the Owner itself is statutorily required to do so. The Consultant is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. Kind Attn.: Sr. DGM (CS-G3) /Manager (CS-G3) Mobile: +91- 9971399074/9205472330 Email: nrapendra@powergrid.in ; ankit@powergrid.in For execution of the subject Conductor Package CD02, Consultant and Owner/Purchaser shall discharge their duties in accordance with agreement signed between them. Consultant’s scope, interalia covers design, engineering, preparation of specifications including BOQ, technical and commercial bid documents, bid opening & evaluation, award recommendation, preparation of master network including time schedule for various project activities, assist in post award execution of contract, project management activities, supervision of testing & commissioning activities, certification of bills for release of payment by SAPDC, etc. The placement of Award to the Contractor and release of payment of Bills (on Certification by POWERGRID) would rest with SAPDC. |
|  | GCC 2.1.1 | Replace GCC 2.1.1 with the following: In the case of successful Foreign Bidder (i.e. Indian bidder), the award shall be made as follows: (i) First Contract (Supply of Goods from Abroad (i.e. Outside Nepal)): For CIP Entry Border Point supply of all Goods from abroad and Type Tests to be conducted abroad, if any. (ii) Second Contract (Supply of Services from within Nepal): For providing all services i.e. port handling and custom clearance of supplies from abroad, inland transportation, In-transit insurance, loading and delivery at site and Supervision Charges, if applicable and any other services specified in the Contract Documents. Both the contracts will contain a cross fall breach clause specifying that breach of one will constitute breach of the others. In the case of successful Nepalese Bidder, the award shall be made as follows: - First Contract (Supply of Goods from within Nepal): For Ex-Works supply of all Goods and Type Tests to be conducted (whether in Nepal or abroad) - Second Contract (Supply of Services from within Nepal): For providing all services i.e. inland transportation, In-transit insurance, loading and delivery at site and Supervision Charges, if applicable and any other services specified in the Contract Documents. Both the above contract shall contain a cross fall breach clause specifying that breach of one will constitute breach of the other. |
|  | GCC 2.1.3 & 2.1.4 | Deleted as Not Applicable |
|  | GCC 2.9 | Deleted as Not Applicable |
|  | GCC 2.14 | Replace clause GCC 2.14 with the following: Governing Law & its Jurisdiction The Contract shall be governed by and interpreted in accordance with laws of Nepal and the Courts of Nepal shall have exclusive jurisdiction in all maters arising under this Contract. |
|  | GCC 4.1 | Replace clause GCC 4.1 with the following: Time for Completion is the essence of Contract. The Supplier shall commence the delivery of Goods to final destination site and shall attain completion of the delivery of Goods to final destination site in accordance with the time schedule specified in the corresponding Appendix – 4 (Delivery Schedule) to the Contract Agreement or within such extended time to which the Supplier shall be entitled under GCC Clause 32 hereof. |
|  | GCC 5.3 | Replace the existing GCC clause 5.3 with the following: The Supplier shall acquire in its name all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located that are necessary for the performance of the Contract, including, without limitation, visas for the Supplier’s and Subcontractor‟s personnel and entry permits for all imported Supplier’s Equipment. The Supplier shall acquire all other permits, approvals and/or licenses that are not the responsibility of the Purchaser under GCC Sub-Clause 6.1 hereof and that are necessary for the performance of the Contract. Wherever required, the Supplier has to open Liaison office/Bank Account in Nepal complying with all applicable laws and regulations of Government of Nepal. |
|  | GCC 5.4 | Replace the existing GCC clause 5.4 with the following: The Supplier shall comply with all laws in force in Nepal. The laws will include all local, state, national or other laws that affect the performance of the Contract and bind upon the Supplier. The Supplier shall indemnify and hold harmless the Purchaser from and against any and all liabilities, damages, claims, fines, penalties and expenses of whatever nature arising or resulting from the violation of such laws by the Supplier or its personnel, including the Subcontractors and their personnel. |
|  | GCC 9.2.1 | Replace the existing GCC clause 9.2.1 with the following: The Supplier shall, within twenty-eight (28) days of the notification of contract award, provide a security in an amount equal to: a. 110% (one hundred ten percent) of the amount of Advance for CIP Entry Border Point Supplies from abroad (i.e. from outside Nepal). b. 110% (one hundred ten percent) of the amount of Advance for Supply of Goods from within Nepal; The above shall be calculated in accordance with the corresponding Appendix - 1 (Terms and Procedures of Payment) to the Contract Agreement, and in the same currency(ies) with initial validity of up to ninety (90) days beyond the completion of delivery of the Goods at the final destination sites under the Contract. The same shall be extended by the Supplier time to time till ninety (90) days beyond the actual date of completion of delivery of the Goods, as may be required under the Contract. |
|  | GCC 9.3.1 | Replace the existing GCC clause 9.3.1 with the following: The Supplier shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Supplier time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. Apart from the Supplier’s performance security, the Supplier shall be required to arrange additional performance securities, as specified in SCC, within twenty-eight (28) days of the notification of award in favour of the Purchaser in the form acceptable to the Purchaser. In addition to the Performance Security of 10% of the Contract Price, the successful bidder is required to furnish additional performance security(ies), if applicable, as per Clause no. 4 of Joint Deed of Undertaking mentioned at Sl. No. 14 of Section – VI: Sample Forms and Procedures. |
|  | GCC 9.3.1.2 (b) | Replace the Clause reference GCC 9.3.1.1 appearing in second line with Clause GCC 9.3.1.2(a) |
|  | GCC 9.3.2 | Replace Sub-Clause GCC 9.3.2 The performance security shall, at the Supplier’s option, be in the form of a crossed bank draft/pay order /banker certified cheque in favour of Purchaser as stipulated in SCC or in the Form of unconditional Bank Guarantee attached hereto in the Section VI - Sample Forms and Procedures. |
|  | GCC 9.3.5 | Add new sub Clause GCC 9.3.5 No interest shall be payable by the Purchaser on the performance Security. |
|  | GCC 9.3.6 | Add new sub Clause GCC 9.3.6 During execution of contract the Supplier, after submission of Performance Security in form of a crossed bank draft/pay order /banker certified cheque, may opt to furnish the Performance Security in form of bank guarantee for the same amount and as per same terms of the Contract. On acceptance by the Purchaser of Performance Security submitted in the form of Bank Guarantee following receipt of confirmation from the issuing Bank, the said amount shall be refunded. |
|  | GCC 9.4 | Replace the existing GCC clause 9.4 with the following: Issuing Banks The Advance Payment Security and Performance Security are to be provided by the Contractor in the form of ‘Bank Guarantee’ which should be issued either: (a) by a reputed bank located in the country of Employer and acceptable to the Employer, or (b) by a foreign bank counter guaranteed by either its correspondent bank located in the country of Employer which should be reputed and acceptable to the Employer, or (c) by a Public Sector Bank in the country of Employer. All banks except Public Sector Banks of the Employer's country shall have with overall international corporate rating or rating of long-term debt not less than A- (A minus) or equivalent by a reputed rating agency. |
|  | GCC 10 | Replacing the existing GCC Clause 10 with the following: 10.1 For CIP Entry Border Point Contract, the Supplier shall be entirely responsible for payment of all taxes, stamp duties, licence fees and other such levies imposed out-side Nepal. In case of Contract for domestic (i.e. from within Nepal) supplies and services, the Supplier shall be entirely responsible for payment of all taxes, duties, licence fees and other such levies legally payable/incurred until delivery of the contracted supplies to the Purchaser. If it is statutory requirement to make deductions towards such taxes and duties or any other applicable taxes and duties, the same shall be made by the Purchaser and a certificate for the same shall be issued to the Supplier. 10.2 The Supplier shall be solely responsible for the taxes that may be levied on the Supplier's persons or on earnings of any of his employees and shall hold the Purchaser indemnified and harmless against any claims that may be made against the Purchaser. The Purchaser does not take any responsibility whatsoever regarding taxes under Income Tax Act of Nepal, for the Supplier or his personnel. If it is obligatory under the provisions of the Income Tax Act, deduction of Income Tax at source shall be made by the Purchaser. 10.3 For CIP Border Point Contract: In case of Supply of Goods & Services from abroad, taxes & duties shall be as follows: (i) any Customs duties/Bhansar or levies or other taxes levied by the Government of Nepal or any local authority in Nepal on the goods and materials covered in the Contract to be imported into Nepal against Purchaser's Import Licence and which will become the property of the Purchaser under the Contract, shall be to the Supplier's account and shall be paid directly by the Supplier to Government of Nepal or concerned authorities. The Supplier shall submit all the requisite documents to enable the Purchaser to obtain the concessional rate of customs and import duties (if applicable). Any additional liabilities of custom and import duties or penalty thereon, due to discrepancy in the said documents or any other lapse of the Supplier shall be to the account of the Supplier. Supplier has to bear all the taxes and duties applicable on the Goods supplied from Abroad. In terms of Project Development Agreement signed between Government of Nepal (GoN) and Purchaser on 24.11.2014, the GoN shall exempt import of cement, iron and steel products from payment of customs duty, subject to compliance of norms of Investment Board of Nepal (IBN). The amount of exemption shall be limited to 50% of the rate of custom duty prevailing as on the date of PDA or the actual rate of custom duty, whichever is lower. The Supplier shall take all steps necessary for obtaining the above exemption and coordinate with concerned authorities of GoN. The Purchaser shall not be liable if Supplier fails to obtain such exemptions from GoN. In addition to above bidders are requested to consider exemptions as per Hydro Development Policy of Nepal 2001 which is available at www.doed.gov.np. For local supplies: In respect of Supply of Goods from within Nepal to the Purchaser by the Supplier, the EXW price is inclusive of all cost as well as duties and tax (ex. custom duties & levies, duties, etc.) paid or payable on the Goods or its components, raw materials and any other items used for their consumption incorporated or to be incorporated in the Goods. Supplier has to bear all the taxes and duties applicable on the Goods supplied from within Nepal. Type test charges for type tests to be conducted in Nepal, if applicable, is inclusive of all the applicable taxes and duties. Supplier has to bear all the taxes and duties applicable on the Type Test charges. 10.4 Further, the price for supply of services from within Nepal for ex. Port handling and customs clearance, Supervision Charges (if applicable), Inland transportation, In-transit Insurance and loading etc, are inclusive of all the taxes and duties. Supplier has to bear all the taxes and duties applicable on all the services. 10.5 Purchaser would not bear any liability on account of any taxes duties, levies applicable on Supply of Goods and Supply of Services Contracts. 10.6 Purchaser shall, deduct taxes at source as per the applicable laws/rules, if any, and issue Tax Deduction at Source (TDS) Certificate to the Supplier. 10.7 Foreign Supplier to ensure PAN/VAT/Company registration of their firm in Nepal as per prevailing acts in Nepal after award of work, if applicable. 10.8 The Supplier shall comply with all tax laws in force in Nepal. The Supplier shall indemnify and hold harmless the Purchaser from and against any and all liabilities, interest, damages, claims, fines, penalties and expenses of whatever nature arising or resulting from the violation of such tax laws by the Supplier or its personnel, including the Subcontractors and their personnel. 10.9 For the purpose of the Contract, it is agreed that the Contract Price specified in Article 2(Contract Price and Terms of Payment) of the Contract Agreement is based on the taxes, duties, levies and charges prevailing at the date seven (07) days prior to the last date of bid submission (hereinafter called “Tax” in this GCC Sub-clause 10.9). If any rates of Tax are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation except for classification related purpose or application of any Tax occurs in the course of the performance of the Contract, which was or will be assessed on the Supplier in connection with performance of the Contract, an equitable adjustment of the Contract price shall be made to fully take into account any such change by addition to the Contract price or deduction therefrom, as the case may be, in accordance with GCC Clause 29 (Changes in Laws and Regulations) hereof. These adjustments shall be applicable for all transactions between the Supplier and the Purchaser for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. and on account of variation in taxes, duties & levies applicable locally. In respect of raw materials, intermediary components etc., the taxes, duties & levies applicable locally, neither the Purchaser nor the Supplier shall be entitled to any claim arising due to increase or decrease in the rate of Tax, introduction of a new Tax or abolition of an existing Tax in the course of the performance of the Contract. |
|  | GCC 15.5 | Adding New sub clause GCC 15.5 The Contractor shall sign the Integrity Pact with its Subcontractors before employing under the Contract. |
|  | GCC 17 | Supplementing GCC 17 with the following: All the acts/laws/rules mentioned hereunder shall be dealt as per corresponding Nepal Government’s applicable acts/laws/rules. |
|  | GCC 17.2.2 | Replacing the GCC 17.2.2 with the following: Unless otherwise provided in the Contract, the Supplier shall be entitled to select any safe mode of transport operated by any person to carry the Goods. In case of transportation by road, the Supplier shall transport all the goods only through registered common carriers in line with requisite Act/rule/notification including amendment thereof. |
|  | GCC 21.1 | Supplementing the Clause GCC 21.1 with the following: The delivery schedule (i.e., Receipt at Site) for the Goods and Related Services to be supplied under the subject packages shall be as follows: Mile Stones; Duration in days from the effective date of Contract (date of Notification of Award; Conductor Quantity to be supplied in Km; Cumulative Conductor Quantity to be supplied in Km; Remarks. Delivery of Goods by the Supplier at final destination site for Conductor Package - CD01 (Spec. No.: CC/NT/G-COND/DOM/A02/25/01011):. 1st; 135 days; 500 Km; 500 Km; The Bidder/Supplier is required to supply the Quantity mentioned as per time schedule. The quantities mentioned are minimum i.r.o each milestone, however, bidder/Supplier may supply additional quantities i.e. upto 2799 Km.. 2nd; 180 days; 1000 Km; 1500 Km. 3rd; 270 days; 1299 Km; 2799 Km. Total Conductor Quantity to be supplied; 2799 Km; 2799 Km. |
|  | GCC 22.2 | Replace Clause GCC 21.2 with the following: 21.2 If the Supplier fails to comply with the Delivery Schedule in accordance with Clause GCC 21 for the whole of the goods, (or a part for which a separate time schedule is agreed) then the Supplier shall pay to the Purchaser a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price of undelivered Goods or the Services as liquidated damages for such default and not as a penalty, without prejudice to the Purchaser's other remedies under the Contract, for each day of delay until actual delivery or performance subject to the limit of ten percent (10%) of Contract Price. The parties agree that the sum specified above is not a penalty but a genuine pre-estimate of the loss/damage which will be suffered by the Purchaser for default on the part of the Supplier and said amount will be payable without proof of actual loss or damage caused by such default. The Purchaser may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Supplier. The payment or deduction of such damages shall not relieve the Supplier from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. Although, the Delivery Schedule has been specified on Milestone basis, for the purpose of levying liquidated damages, the delay in delivery shall be considered on a quarterly basis, the quarter being reckoned from the first month of dispatch. |
|  | GCC 22.1 | Replacing Sub-Clause GCC 22.1 - The Defect Liability Period shall remain valid for a period of twelve (12) months from the date of commissioning of Goods or Eighteen (18) months from the date of completion of delivery at final destination site(s) whichever is earlier. |
|  | GCC 23 | Deleted as Liquidated Damages for Non-Performance of Equipment are not applicable. |
|  | GCC 26.1 | Replacing sub clause GCC 26.1 with the following: Ownership of the Goods to be imported into Nepal shall be transferred to the Purchaser upon loading on to the mode of transport to be used to convey the Goods from the country of origin to that country and upon endorsement of the dispatch documents in favour of the Purchaser. |
|  | GCC 26.2 | Replacing sub clause GCC 26.2 with the following: Ownership of the Goods procured in Nepal, shall be transferred to the Purchaser upon loading on to the mode of transport to be used to carry the Goods from the works/warehouse/ any other place where the Supplier wishes to supply the goods to the site and upon endorsement of the despatch documents in favour of the Purchaser. |
|  | GCC 28.1 (a)(I)(ii) | Replacing sub clause GCC 28.1 (a)(I)(ii) with the following: Transit Insurance Policy for indigenous equipment Similarly, Transit Insurance Policy shall be taken wherein only inland transit is involved for the movement of Goods supplied from within Nepal. The policy shall cover movement of Goods from the manufacturer’s works to the project’s warehouse at final destination site. The perils required to be covered under the insurance shall include, but not be limited to, fire and allied risks, miscellaneous accidents, workman compensation risks, loss or damage in transit, theft, pilferage, riots and strikes and malicious damages, civil commotion, weather conditions, accidents of all kinds, war risks (as far as insurable) etc. Inland Transit Clause (ITC) “A” alongwith Strike Riots & Civil Commotion (SRCC) extension cover shall be taken. |
|  | GCC 29.1 | Replacing sub clause GCC 29.1 with the following: If, after the date seven (07) days prior to the date of Bid Opening, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed in Nepal (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Supplier and/or the Delivery Schedule, the Contract Price shall be correspondingly increased or decreased, and/or the Delivery Schedule shall be reasonably adjusted to the extent that the Supplier has thereby been affected in the performance of any of its obligations under the Contract. These adjustments shall be applicable for all transactions between the Purchaser and the Supplier for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Supplier for which the Purchaser shall be the sole judge. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the Appendix-2 to the Contract Agreement. |
|  | GCC 31.2.1 | Deleted as not applicable. |
|  | GCC 33.1.3 | Replacing sub clause GCC 33.1.3 with the following: if the Contractor, in the judgment of the Purchaser/Consultant has violated the ‘Code of Integrity for Public Procurement’ attached as Appendix-II to the Special Conditions of Contract, in competing for or in executing the Contract. In persuasions to its policy for ‘Code of Integrity for Public Procurement’, the Purchaser/Consultant will take appropriate measures in line with the above policy if it determines that the firm has, directly or through an agent, violated this Code of Integrity in competing for or in executing, the contract in question. |
|  | GCC 36.2 to 36.5 | Delete following sub paras: GCC 36.2, 36.3, 36.4, 36.5. |
|  | GCC 36.2 | Add new sub para GCC 36.2: Any dispute or difference whatsoever arising between the parties and of or relating to the construction, interpretation, application, meaning, scope, operation or effect of this Contract or the validity or the breach thereof, shall be settled by arbitration in accordance with Nepal Arbitration Act 2055 (1999) and the Rules of Arbitration of the Institution i.e SCOPE Forum of Concillation and Arbitration (SFCA), New Delhi. The cost and expenses of Arbitration proceedings will be borne by each party as per terms of Institution. However, the expenses incurred by each party in connection with the preparation, presentation etc. of its proceedings shall be borne by each Party itself. Provided always that no reference for arbitration shall be maintainable unless the Contractor deposits to the Employer a sum equal to 1.0 % (one percent) of the amount under dispute and the sum so deposited shall, on the termination of the arbitration proceedings be adjusted against the cost, if any, awarded by the arbitral tribunal against the Contractor and the balance remaining after such adjustment or in the absence of any such cost being awarded, the whole of the sum will be refunded to him within one month from the date of the arbitral award. No interest shall be paid by the Employer on the amount deposited by the Contractor for referring the claim to arbitration. Performance under the Contract shall continue during the arbitration proceedings and payments due to the Contractor by the owners shall not be withheld, unless they are the subject matter of the arbitration proceedings. The Arbitral Tribunal shall give a written reasoned Award and the final award by a majority of Arbitrators rendered in writing shall be binding upon the parties. |
|  | GCC 36.3 & 36.4 | Existing clauses GCC 36.6 & 36.7 are renumbered as GCC 36.3 & 36.4, respectively. |
|  | GCC 37 | Add new Clause GCC clause 37 in Section-V (SCC): 37.0 POWERGRID Whistle Blower and Fraud Prevention Policy The Supplier along with its associate/ collaborators/ sub-contractors/ sub-vendors/consultants/ service providers shall strictly adhere to the Whistle Blower and Fraud Prevention Policy of Purchaser/Consultant displayed on its tender website https://apps.powergrid.in/pgciltenders/u/default.aspx and https://www.powergrid.in/index.php/en/code-conductpolicies. The Supplier along with their associate / collaborator / subcontractors / sub-vendors / consultants / service providers shall observe the highest standard of ethics and shall not indulge or allow anybody else working in their organization to indulge in fraudulent activities during execution of the contract. The contractor shall immediately apprise the Purchaser/Consultant about any fraud or suspected fraud as soon as it comes to their notice. |

----- End of Section-V (SCC) ----